## Лист1
Kokhanov, Yeremenko, Tkachov, Daubur, Danilenko, Kiparenko, Golubchikov
SPRINT BACKLOG |  | # PRJ-PM113
Ask Service |  | AS OF 2014-10-03
UserStory | Task | Status | Estimate | Валерий | Дмитрий | Кирилл | Сергей | Евгений | Игорь | Александр
As an unregistred user, I want to authorize from my other social network accounts | As a registred user, I want to attach twitter.com account | Verify | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| As a registred user, I want to attach Google+ account | Verify | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
As a user, I want to search registred users` pages | search registred users` pages by keywords | Verify | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| filter the list of registred users` pages | Verify | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
As a registred user, I want to get statistic information about my account | view number of my answers | Verify | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| view number of my questions | Verify | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| view number of my likes | Verify | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
As a registred user, I want to control my profile | As a registred user, I want to add my mude to my page | Verify | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Burndown Chat Diagram
|  | Day | Done | Remaining | Ideal Done per Day | Ideal Velocity
|  | 0 | 0 | 24 | 4 | 24
|  | 1 | 2 | 22 | 4 | 20
|  | 2 | 4 | 18 | 4 | 16
|  | 3 | 4 | 14 | 4 | 12
|  | 4 | 6 | 8 | 4 | 8
|  | 5 | 4 | 4 | 4 | 4
|  | 6 | 4 | 0 | 4 | 0