## Лист1
Kokhanov, Yeremenko, Tkachov, Daubur, Danilenko, Kiparenko, Golubchikov
SPRINT BACKLOG |  | # PRJ-PM113
Ask Service |  | AS OF 2014-10-03
UserStory | Task | Status | Estimate | Валерий | Дмитрий | Кирилл | Сергей | Евгений | Игорь | Александр
As an unregistred user, I want to authorize from my other social network accounts | Implement, authorize from vk.com | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Implement, authorize from twitter.com | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
As a registred user, I want to attach my social network accounts | As a registred user, I want to attach vk.com account | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| As a registred user, I want to attach facebook.com account | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
As a registred user, I want to control my profile | change my personal information | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| set privacy of my personal information | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
As an unregistred user, I want to send anonimus questions to registerd users | Implement, question special box on a user`s wall | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Realize button for sending introduced question | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
As an admin, I want to control question list | view the list of users` questions | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| choose user`s question | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| answer chosen user`s question | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
As a registred user, I want to follow registred users` pages | follow the page, I am interested in | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Burndown Chat Diagram
|  | Day | Done | Remaining | Ideal Done per Day | Ideal Velocity
|  | 0 | 0 | 50 | 5 | 50
|  | 1 | 4 | 46 | 5 | 45
|  | 2 | 4 | 42 | 5 | 40
|  | 3 | 6 | 36 | 5 | 35
|  | 4 | 5 | 31 | 5 | 30
|  | 5 | 4 | 27 | 5 | 25
|  | 6 | 4 | 23 | 5 | 20
|  | 7 | 6 | 17 | 5 | 15
|  | 8 | 6 | 11 | 5 | 10
|  | 9 | 5 | 6 | 5 | 5
|  | 10 | 6 | 0 | 5 | 0