## Sheet1
Kokhanov, Yeremenko, Tkachov, Daubur, Danilenko, Kiparenko, Golubchikov
PROJECT BACKLOG |  |  |  |  | # PRJ-PM113
Ask Service |  |  |  |  | AS OF 2014-10-03
В пункте меню "Личный кабинет" нажать "Мои курсы" выбрать интересующий курс и нажать "Оценить" справа от названия курса, после чего откроется страница для выставления рейтинговых оценок по категориям, оценив курс по данным критериям нажать "ОК" | Imp | Iteration | Status | Name | How to demo / Notes | Estimate | Comments
| High |  |  | As an unregistered user, I want to browse users' pages |  | 10
1 |  | Valera |  | Implement, choose registered user | I choose a registered user and clicking on its icon turn on his page | 2
2 |  | Valera |  | Implement, browse registered user`s wall | I look through the wall will register the user box on his page | 5
3 |  |  |  | Implement, browse registered user`s profile, if it is not hidden | If the page the user is not hidden, I can see all the information about the user and his wall with questions | 3
| Medium |  |  | As an unregistered user, I want to authorize from my other social network accounts |  | 20
4 |  | Evgeniy |  | Implement, authorize from vk.com | To login to the site I can use the social network vk.com by clicking on the appropriate button for the icon of the social network | 5
5 |  | Evgeniy |  | Implement, authorize from facebook.com | To login to the site I can use the social network facebook.com clicking on the appropriate button for the icon of the social network | 5
6 |  |  |  | Implement, authorize from twitter.com | To login to the site I can use the social network twitter.com clicking on the appropriate button for the icon of the social network | 5
7 |  |  |  | Implement, authorize from myspace.com | To login to the site I can use a social network myspace.com clicking on the appropriate button for the icon of the social network | 5
| High |  |  | As an unregistered user, I want to register through the website |  | 4
8 |  | Dima |  | Create, textbox for registred login and password | In the fields of registration enter your login and password for registration | 1
9 |  | Dima |  | Create, textboxes for personal data (name, surname, age, sex) | In the appropriate fields when registering to enter your name, surname, age, date of birth for display on the main page. | 3
| Medium |  |  | As an unregistered user, I want to send anonimus questions to registerd users |  | 8
10 |  | Jenya |  | Implement, question special box on a user`s wall | In a special field to enter the issue page owner, you can enter a question. | 5
11 |  | Jenya |  | Realize button for sending introduced question | Permission message I can send it to the user clicking on the appropriate button next to the input field | 3
| Medium |  |  | As a registred user, I want to choose message sending mode |  | 8
12 |  | Sergey |  | Implement, checkbox for choose anonimus message sending mode | Selecting the type of message, namely anonymous by selecting it in the checkbox, send the user a message anonymously | 5
13 |  | Sergey |  | Implement, choose common message sending mode | In the input box enter the question without selecting checkbox anonymous input | 3
| High |  |  | As a registred user, I want to control my wall |  | 8
14 |  |  |  | Realize button for delete questions | The answer to my wall I delete by clicking on the appropriate "cross" removal in the upper right corner. | 3
15 |  |  |  | As a registred user, I want to add answers | To a question in the answer I enter your answer and press the button to send a reply to the question appears on my wall | 5
| Medium |  |  | As a registred user, I want to rate users` answers |  | 13
16 |  |  |  | As a registred user, I want to like answers | By clicking on the "star" can be estimated like the answer | 8
17 |  |  |  | As a registred user, I want to cancel my likes | If the answer was rated by you then when you click on the "star" I can cancel my Like | 5
| Low |  |  | As a registred user, I want to attach my social network accounts |  | 12
18 |  |  |  | As a registered user, I want to attach vk.com account | In the settings of your account by clicking on the icon in the social network vk.com can attach your account with a social network | 3
19 |  |  |  | As a registered user, I want to attach facebook.com account | In the settings of your account by clicking on the icon of the social network facebook.com, you can attach your account with a social network | 3
20 |  |  |  | As a registered user, I want to attach myspace.com account | In the settings of your account by clicking on the icon of a social network myspace.com you can attach your account with a social network | 3
21 |  |  |  | As a registered user, I want to attach twitter.com account | In the settings of your account by clicking on the icon in the social network twitter.com you can attach your account with a social network | 3
| High |  |  | As a registered user, I want to control my friendlist |  | 11
22 |  | Igor |  | As a registered user, I want to add a registerd user to my friendlist | Being on the other page and clicking on the "Add as friend" button, you can add this user to your friends list | 8
23 |  |  |  | As a rsuser, I want to delete a registerd user to my friendlist | When you click on the delete button opposite to each other in the friends list, you can delete it from the list | 3
| Medium |  |  | As a registred user, I want to control my profile |  | 18
24 |  |  |  | As a registered user, I want to change background of my page | In the settings of your page I can choose the background, different, or upload an image from your computer and use it as a background | 8
25 |  |  |  | As a registered user, I want to add my mude to my page | I can add status to your page that will be displayed on my page | 2
26 |  | Valera |  | change my personal information | To change the information in your account you must double click on the relevant box and enter new data. | 5
27 |  |  |  | set privacy of my personal information | To change the display of the personal data in your account, you select one of the following items: "Show all information", "Show information only friends", "Do not show anyone." | 3
| High |  |  | As a registred user, I want to answer incoming questions |  | 11
28 |  |  |  | view incoming questions list | When you click on the main transition occurs on the page with a sheet of questions that came to this account | 5
29 |  |  |  | choose incoming question, I want to answer | To do this, click on the question, the display for the answer to the question, for the answer to another question, repeat the operation | 3
30 |  | Kirill |  | write an answer on chosen question | This information will be under each entry | 3
| Low |  |  | As a registred user, I want to get statistic information about my account |  | 6
31 |  |  | Kiparenko | view number of my answers | To see the number of responses, you need to look in the "Your answers" in the upper right corner at the beginning of the wall | 2
32 |  |  | Kiparenko | view number of my questions | To see the number of responses, you need to look in the "Your Questions" in the upper right corner at the beginning of the wall | 2
33 |  |  | Kiparenko | view number of my likes | To see the number of responses, you need to look in the "Liked" in the upper right corner at the beginning of the wall | 2
| Medium |  |  | As a registred user, I want to follow registered users` pages |  | 5
34 |  |  |  | follow the page, I am interested in | Profile of another user by clicking on the "Subscribe" button occurs subscription to his answers | 5
| Medium |  |  | As a registred user, I want to comment any answer |  | 7
35 |  | Valera |  | choose answer, I want to comment | Profile of another user by clicking on his response to the comments box appears | 2
36 |  |  |  | write a comment a chosen answer | After filling out the field for a comment you need to press the "Add Comment", which will add a comment | 5
| Medium |  |  | As a user, I want to search registered users` pages |  | 10
37 |  |  |  | search registered users` pages by keywords | The search string is entered at which a word search | 5
38 |  |  |  | filter the list of registered users` pages | Filtration is carried out in the fields selected by the user | 5
| High |  |  | As a user, I want to send questions to registered users |  | 4
39 |  | Kirill |  | input my question on user`s page wall | By clicking on the "Ask a question" question sent to the user who asked | 2
40 |  | Kirill |  | send my question | By clicking on the "Ask a question" question sent to the user who asked | 2
| Medium |  |  | As a user, I want to get an administration support |  | 5
41 |  |  |  | report administrator about my problems | In the "Technical Support" is a text input field and a button "Ask a question" | 5
| Medium |  |  | As an admin, I want to provide technical support |  | 8
42 |  |  |  | view the list of users` questions | This information will be on the main profile of the administrator, after clicking on the "Show all questions users" | 3
43 |  |  |  | choose user`s question | To select the question you must click on the content | 2
44 |  |  |  | answer chosen user`s question | To answer the question selected, you must enter the answer in the field in question and click "Reply" | 3
| Low |  |  | As an admin, I want to manage user list |  | 3
45 |  |  |  | delete a registrеd user | To remove a user admin, you need to otkrіt list of users, and near the necessary login click the "Delete" and confirm the deletion | 3
| Medium |  |  | As an admin, I want to provide message delivery |  | 6
46 |  |  |  | deliver question of a day to all users | To enter the question of the day, the admin on the main page says in the text, and the question and nazhimet on the "Subscribe" | 3
47 |  |  |  | deliver system warnings | To write warning comes on the admin page, you need a user clicks on the "Warning" in the box that appears, writes the warning text | 3
| Medium |  |  | As an admin, I want to control users' wall |  | 11
48 |  |  |  | delete suspicious questions and answers | To delete suspicious questions and answers admin comes to the page the user clicks on the desired content and click "Delete" | 8
49 |  |  |  | comment answers with administration warnings | To write warning comes on the admin page, you need a user clicks on the desired content, clicks on the "Warning" in the box that appears, writes the warning text | 5
Note on B5: Note: Unique ID
Note on C5: Note: Importance. High = more importance. Used only for sorting in priority order. (1-5) Only product owner is allowed to set this.
Note on H5: Note: Relative size of this story. Only the team is allowed to set this.