## Лист1
Kokhanov, Yeremenko, Tkachov, Daubur, Danilenko, Kiparenko, Golubchikov
SPRINT BACKLOG |  |  | # PRJ-PM113
Ask Service |  |  | AS OF 2014-10-03
В пункт | UserStory | Task | Estimate | Iteration
1 | As a registred user, I want to comment any answer | Choose answer, I want to comment | 2 | Valera
2 | As a registred user, I want to control my profile | Change my personal information | 5 | Valera
3 | As a registred user, I want to rate users` answers | As a registred user, I want to like answers | 8 | Dima
4 | As a registred user, I want to rate users` answers | As a registred user, I want to cancel my likes | 5 | Dima
5 | As an unregistered user, I want to authorize from my other social network accounts | Implement, authorize from vk.com | 5 | Jenya
6 | As an unregistered user, I want to authorize from my other social network accounts | Implement, authorize from facebook.com | 5 | Jenya
7 | As a registred user, I want to control my wall | Realize button for delete questions | 3 | Sergey
8 | As a registred user, I want to control my wall | As a registred user, I want to add answers | 5 | Sergey
9 | As a registered user, I want to control my friendlist | As a user, I want to delete a registred user to my friendlist | 3 | Igor`
10 | As a registred user, I want to control my profile | As a registered user, I want to add my mude to my page | 2 | Igor`
11 | As a registred user, I want to control my profile | Set privacy of my personal information | 3 | Igor`
12 | As a user, I want to get an administration support | report administrator about my problems | 5 | Aleksandr
13 | As an admin, I want to provide technical support | view the list of users` questions | 3 | Aleksandr
14 | As an admin, I want to manage user list | delete a registrеd user | 3 | Kirill