## Лист1
Kokhanov, Yeremenko, Tkachov, Daubur, Danilenko, Kiparenko, Golubchikov
SPRINT BACKLOG |  | # PRJ-PM113
Ask Service |  | AS OF 2014-10-03
UserStory | Task | Status | Estimate | Валерий | Дмитрий | Кирилл | Сергей | Евгений | Игорь | Александр
As an unregistered user, I want to browse users' pages | Implement, choose registered user | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement, browse registered user`s wall | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
As an unregistered user, I want to register through the website | Create, textbox for registred login and password | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Create, textboxes for personal data (name, surname, age, sex) | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
As a registred user, I want to control my wall | As a registred user, I want to add answers | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Realize button for delete questions | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
As a registred user, I want to choose message sending mode | Implement, checkbox for choose anonimus message sending mode | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Implement, choose common message sending mode | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
As a registred user, I want to answer incoming questions | choose incoming question, I want to answer | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| view incoming questions list | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| write an answer on chosen question | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
As a user, I want to send questions to registred users | input my question on user`s page wall | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| send my question | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
As a registered user, I want to control my friendlist | As a registered user, I want to add a registred user to my friendlist | Done | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Burndown Chat Diagram
|  |  | Day | Done | Remaining | Ideal Done per Day | Ideal Velocity
|  |  | 0 | 0 | 50 | 5 | 50
|  |  | 1 | 0 | 50 | 5 | 45
|  |  | 2 | 0 | 50 | 5 | 40
|  |  | 3 | 4 | 46 | 5 | 35
|  |  | 4 | 8 | 38 | 5 | 30
|  |  | 5 | 8 | 30 | 5 | 25
|  |  | 6 | 6 | 24 | 5 | 20
|  |  | 7 | 4 | 20 | 5 | 15
|  |  | 8 | 8 | 12 | 5 | 10
|  |  | 9 | 4 | 8 | 5 | 5
|  |  | 10 | 8 | 0 | 5 | 0