## Лист1
Kokhanov, Yeremenko, Tkachov, Daubur, Danilenko, Kiparenko, Golubchikov
SPRINT BACKLOG |  | # PRJ-PM113
Ask Service |  | AS OF 2014-10-03
UserStory | Task | Status | Estimate | Валерий | Дмитрий | Кирилл | Сергей | Евгений | Игорь | Александр
As an unregistered user, I want to browse users' pages | Implement, browse registred user`s profile, if it is not hidden | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
As a registred user, I want to rate users` answers | As a registred user, I want to like answers | Done | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| As a registred user, I want to cancel my likes | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
As an unregistred user, I want to authorize from my other social network accounts | Implement, authorize from facebook.com | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Implement, authorize from Google+ | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
As a registred user, I want to control my profile | As a registred user, I want to change background of my page | Done | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
As a registred user, I want to comment any answer | choose answer, I want to comment | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| write a comment a chosen answer | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
As a registred user, I want to control my friendlist | As a user, I want to delete a registred user to my friendlist | Done | 8 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Burndown Chat Diagram
|  | Day | Done | Remaining | Ideal Done per Day | Ideal Velocity
|  | 0 | 0 | 44 | 5 | 44
|  | 1 | 2 | 42 | 5 | 39
|  | 2 | 4 | 38 | 5 | 34
|  | 3 | 5 | 33 | 5 | 29
|  | 4 | 4 | 29 | 5 | 24
|  | 5 | 6 | 23 | 5 | 19
|  | 6 | 8 | 15 | 5 | 14
|  | 7 | 5 | 10 | 5 | 9
|  | 8 | 2 | 8 | 5 | 4
|  | 9 | 4 | 4 | 5 | 0
|  | 10 | 4 | 0 | 5 | 0